## Gantt
Webpage gantt chart |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
| Start Date | End date | Duration in days | Team | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
Pre-development phase | bar: Week 1 M 4 to Week 3 M 18
Collect information from customer | 2020-05-04 | 2020-05-18 | 15 | Information | bar: Week 1 M 4 to Week 3 M 18
Make a plan | 2020-05-04 | 2020-05-07 | 4 | Design | bar: Week 1 M 4 to Week 2 F 15
Create a mockup/wireframe of webpage | 2020-05-04 | 2020-05-05 | 2 | All teams | bar: Week 1 M 4 to Week 1 T 5
Meeting with customer. | 2020-05-06 | 2020-05-06 | 1 | All teams | bar: Week 1 W 6
Webpage development start - presentation | 2020-05-07 | 2020-05-08 | 2 | Dev + design | bar: Week 1 Th 7 to Week 2 F 15
Main Development phase
Create home page | 2020-05-11 | 2020-05-13 | 3 | All teams
Make home page | 2020-05-11 | 2020-05-11 | 1 | All teams
Subscribe to the company | 2020-05-11 | 2020-05-11 | 1 | Dev
Full-text search window | 2020-05-11 | 2020-05-13 | 3 | Dev
Make an text writer program for user | 2020-05-11 | 2020-05-13 | 3 | Dev
Create Product and order page | 2020-05-12 | 2020-05-15 | 4 | All teams
Add product to cart | 2020-05-12 | 2020-05-12 | 1 | Dev
Remote product from cart | 2020-05-12 | 2020-05-12 | 1 | Dev
Payment options visa/debit card. Invoice. | 2020-05-12 | 2020-05-15 | 4 | Dev
Payment option PayPal | 2020-05-12 | 2020-05-15 | 4 | Dev
Order shipping option | 2020-05-12 | 2020-05-15 | 4 | Dev
Create about us page | 2020-05-15 | 2020-05-15 | 1 | Dev + design
Create contact page | 2020-05-15 | 2020-05-15 | 1 | Dev + design
Faq content. | 2020-05-15 | 2020-05-22 | 8 | Dev + Information | bar: Week 2 M 11 to Week 3 F 22
Make a contact form, code to send a email. | 2020-05-15 | 2020-05-15 | 1 | Dev
Create promotion | 2020-05-15 | 2020-05-22 | 8 | Information + Design | bar: Week 2 M 11 to Week 3 F 22
Testing and presentation
Review of the pages. | 2020-05-18 | 2020-05-21 | 4 | Dev | bar: Week 2 M 11 to Week 3 Th 21
Troubleshoot code | 2020-05-18 | 2020-05-20 | 3 | Dev + design | bar: Week 2 M 11 to Week 3 W 20
Presentation for customer | 2020-05-21 | 2020-05-22 | 2 | All teams | bar: Week 3 Th 21 to Week 3 F 22
Final review
Test webpage | 2020-05-21 | 2020-05-21 | 1 | Dev + Design | bar: Week 3 Th 21
Minimize code | 2020-05-21 | 2020-05-25 | 5 | Dev | bar: Week 3 Th 21 to Week 4 M 25
Lauch of webpage | 2020-05-25 | 2020-05-26 | 2 | Dev | bar: Week 4 M 25 to Week 4 T 26